## BA Test Script
Yahoo! Online Protection/YOP - Norton Security/NIS Online 2007 Requirements BA Test Script Originally created by Phillip Pi
| Brief Description | Steps/Instructions | Results | Estimated Time (minutes) | Notes
1 | Set it up. | 1. Use a supported Windows [XP (non-server and 32-bit only) and Vista (32-bit and 64-bit)]. Change this often to vary the installs. 2. Be sure user is logged in with administrator access and not in safe mode. 3. Copy/Extract NSO. | 1. Set up the operating system/OS. 2. Can't install without administrator access. 3. Set up the layout and installer for NSO. | 5 | YOP software installer will output any error message, not from Symantec's installer
2 | Check to see if Yahoo!'s layout has these lines and values in its inopts.dat file. | Check Yahoo!'s NSO layout for setup\instopts.dat file. View this file with optionsedit.exe tool. Look for the entries and their DWORD values: CFGWIZ:ShowLaunchLiveUpdate = 0 CFGWIZ:SilentMode = 1 INSTALL:EnableAutoProtect = 0 INSTALL:NoDeskTopIcon = 1 INSTALL:NoReboot = 1 INSTALL:ShortcutMenu = 0 INSTALL:WebProtection = 0 INSTOPTS:BlockInteScan =1 INSTOPTS:EnableAutoLiveUpdate = 0 INSTOPTS:HideFromAddRemove = 1 INSTOPTS:LaunchCfgWiz = 0 INSTOPTS:LaunchUI = 0 INSTOPTS:ReturnCodeInReg = 1 ui:NSCSystray = 1 | Be sure instopts.dat file has the correct lines and values. | 5 | From Julio Cuellar's e-mail sent on November 28, 2006 12:21 PM PST. INSTALL:NoReboot = 1 addresses the /ReallyReboot command line switch. --Julio Cuellar's 11/29/2006 3:09 PM e-mail.
3 | Verify that the differences between the files… | 1. Bindiff YOP NSO's layout against the NSO generic layout. 2. Use Araxis or another tool (e.g., windiff) to compare the cltdist.ini file between generic SOS NIS full layout vs. SOS NIS no web protection (e.g., YOP layout). | 1. See if any differences to cause problems. 2. Verify that the only difference is the branding for no web protection. More values might be different depending upon the base layout licensing configuration. | 15
4 | Installation of NSO. | 1. Silent extract ESD EXE and install with: Install_NortonSecurityOnline_Yahoo_Production.exe /qn -y /O INSTALLDIR="path here" like Install_NortonSecurityOnline_Yahoo_Production.exe /qn -y /O INSTALLDIR="C:\Program Files\Yahoo! Online Protection" 2. If Windows XP doesn't have the required or newer version of MSI (msiexec.exe v3.1.4000.18 is required), then MSI will be upgraded to v3.1.4000.18. 3. Make sure the product installs in the customized directory/folder (if success). 4. Either the installation was a success or a failure. 5. After installation, there should be NO reboot required. | 1. Silent extract and install doesn't show any GUI (some errors might not be suppressable though). Watch extraction and symsetup.exe to see when it is done (disappears). 2. Check for MSI for requirement and upgrade it if necessary. 3.-4. Be sure the installation didn't fail. If it failed in silent install, then be sure no log collection and reporter come up. 5. No reboot yet. | 10 | Based on: symsetup.exe /qn /O INSTALLDIR="<custom folder/directory>" The -y is a new one to suppress any error message boxes, use the -y switch on the self extracting executable. It has not been tested, make sure it works. DWORD value under the Windows' registry HKLM\Software\Symantec\SymSetup key: SuppressReboot to 1 before uninstalling any given product. symsetup.exe /qn /O REBOOT=ReallySuppress is for silent NIS/NSO install without a reboot. Note: No need to use the REBOOT=ReallySuppress flag since the layout is pre-configured through an instopts.
5 | Check for installed and missing files and registry datas. | 1. After installing NSO successfully, run InstallCheck tool with the latest filelist (INI). 2. Check all file signatures and time stamps. Pay extra attention to the files listed below since these get modify by Scott Whitney in every build: -isRes.dll (EULA) -isStatus.loc -NISOpRes.dll (Title panel) -pcStatus.loc -UiCntnr.loc | Ensure all files and registry datas are found. | 10
6 | Error code from successful or failed install. | 1. After failing to install NSO (e.g., run another Windows account in the background), check Windows' registry's (HKEY_LOCAL_MACHINE\SOFTWARE\Symantec\SymSetup\ReturnCode\SymSetupRetCode = <a non-zero number>) 2. Fix the problem(s) and install NSO successfully, then check the same registry key. | Windows' registry in its HKEY_LOCAL_MACHINE\SOFTWARE\Symantec\SymSetup\ReturnCode\SymSetupRetCode should show its install result value (e.g., 0 for success. All others are failures, problems, etc.). These error codes are found by YOP's software installer. | 15 | There's a list of code values and what they mean. 0 means success (no problems).
7 | CfgWiz | 1. CfgWiz should NOT launch (loud) or execute silently by itself after installation, manually execute configwiz (remember to include the quotes): "C:\Program Files\Common Files\Symantec Shared\OPC\{31011D49-D90C-4da0-878B-78D28AD507AF}\cltUIStb.exe" /MODULE CfgWiz /GUID {BC8D3EAF-F864-4d4b-AB4D-B3D0C32E2840} /MODE CfgWiz /CMDLINE "REBOOT". 2. Make sure that CfgWiz executes silently (check Cfgwiz.exe at task bar and task manager; no pop-ups). Cfgwiz.exe should not hang. 3. Check in Windows' registry for HKLM\Software\Symantec\PartnerInfo\CfgWizSuccess = 1 4. Check the CFGWIZ:Finished = 1 result in cfgwiz.dat (use optionsedit.exe tool) after installation. | CfgWiz automatically configures and silently. | 10
8 | Activation | After CfgWiz, Run tool (ask Sidd's registry file to import and instructions) to silently activate NSO by calling the silent activation API. Try failing (e.g., no internet connection) and successfully alternatively in tests. Note activation stuff is not via CfgWiz like in previous NIS. | Ensure the behaviors and results are correct. | 5 | If using with YOP, then this will be automatic right after installation. "Configwiz and Activation will be decoupled. Yahoo will call Configwiz to execute silently. After Yahoo checks the successful completion, they will call the Silent activation API that Jack is working on." --Julio Cuellar's e-mail reply (11/29/2006 1:43 PM PST).
9 | LiveUpdate | After CfgWiz, LiveUpdate (LUall.exe only) runs by itself from Yahoo!. Note that Yahoo! software controls this part. However, the user can pretend this works by running luall.exe. | All updates should look correct, downloaded, and installed successfully. Reboot as needed and is fine. | 5 | LiveUpdate right after installation and CfgWiz might want a reboot. This is fine.
10 | Ensure NSO is basically NIS w/o web protection. Web protection feature is part of NCO. It’s also called “fraud protection”, it’s the anti-phishing piece of NCO [toolbar]. | Ensure its Web protection/NCO is disabled and... 1. “Transaction Security” section on the main (NPC) page is grayed out (but not hidden, due to design limitations). 2. “Phishing Protection” category in the NIS/NSO's Settings page/section is hidden. 3. Web Protection category would not generate alerts. 4. NCO Toolbar in Internet Explorer (IE) is not shown/available. Also, close IE, disable NAV's AP, relaunch IE. Do the same, but re-enable NAV AP and recheck IE. 5. The Web protection files are not installed. All files that are installed by Browser.msi & WebProt.msi are not installed. Basically, see if C:\Program Files\Common Files\Symantec Shared\coShared exists where NCO are installed. Also, NCO's help files (nco*.* I think; do a search in help for phishing, confidiential, etc.). | Be sure that each item show the correct behaviors in the steps/instructions. | 15 | The “Transaction Security” section on the main (NPC) page is grayed out (but not hidden, due to design limitations), the “Phishing Protection” category in the Settings (NIS/NSO) page is hidden, and the Web Protection category would not generate alerts. The Web protection files are not installed. This means all files that are installed by Browser.msi & WebProt.msi are not installed according to Viral Mehta. --Deborah Perri's 11/7/2006 5:07 PM PST e-mail.
11a | instopts.dat's settings vs. installation results for YOP's NSO 2007. | Installation: 1. INSTOPTS:ReturnCodeInReg = 1 ... symsetup writes status code in registry after installation. 2. If installation succeeded, this value should be in the registry (HKEY_LOCAL_MACHINE\SOFTWARE\Symantec\SymSetup\ReturnCode\SymSetupRetCode = 0). | Make sure that each setting is doing what it is suppose to do. | 2
11b |  | CfgWiz: 1. CFGWIZ:SilentMode = 1 ... CfgWiz does not show main UI. 2. INSTOPTS:LaunchCfgWiz = 0 ... Do not launch CfgWiz automatically after installation. YOP will do this. 3. CFGWIZ:ShowLaunchLiveUpdate = 0 ... Don't run LU automatically after installation. | Make sure that each setting is doing what it is suppose to do. | 2
11c |  | Installation and Comestic: 1. INSTALL:EnableAutoProtect = 0 ... No NAV's AutoProtect during installation. 2. INSTALL:NoDeskTopIcon = 1 ... No desktop shortcut icons created. 3. INSTALL:ShortcutMenu = 0 ... No Start Menu shortcuts. 4. INSTALL:WebProtection = 0 ... No NCO and its components like its toolbar in IE. 5. ui:NSCSystray = 1 ... Security Console/NPC goes into system tray icon by default instead of taskbar. | Make sure that each setting is doing what it is suppose to do. | 3
11d |  | Install Options: 1. INSTOPTS:BlockInteScan =1 ... no preinstall scan. 2. INSTOPTS:EnableAutoLiveUpdate = 0 ... Automatic LU is disabled by default. 3. INSTOPTS:HideFromAddRemove = 1 ... No NSO entry in Windows' Add/Remove Programs list. 4. INSTOPTS:LaunchUI = 0 ... main UI does not launch. | Make sure that each setting is doing what it is suppose to do. | 3
12 | Branding and UI Changes | Look around for these things: a. Symantec logo moved to bottom left from its default location in NPC screen. b. No partner co-brand on NPC. c. Customized title bar icon of Main UI with "Norton Security Online provided by Yahoo! Online Protection". d. Display title bar icon (no bar). e. Customized text. f. Norton Protection Center/NPC is a taskbar icon to Windows' systray area. | Ensure that these branding and UI console have changes (look different from original NIS 2007). See notes for other information. | 15 | a. Symantec logo is in the bottom left location corner. b. Etrack #867833. c. The text of the title bar is customizable and can be changed. For example: Change from Symantec to Yahoo Online Protection: Norton Internet Security. Title Bar Text to be used: Norton Security Online provided by Yahoo! Online Protection d. Title bar isn't shown. f. The requirement has been changed to move the NPC icon from the task bar to the systray icon. instopts.dat's ui:NSCSystray line controls this.
13 | Readme and Help | 1. Ensure the Readme in layout and installation. Read them as well. 2. See NSO's help. | Be sure they are correct. | 5
14 | Firewall prompts during NSO installation, configuration, and usage. | When installing, configuring, and using NSO (mainUI -- to run uistub.exe or from NPC's in Windows' task bar), nothing (NSO and YOP) should be blocked by the firewall component. All Internet access/ALE rules should already be made. | No interruptions when using the Internet with NSO. | 5 (should be looking for them during BA testing) | Bryan Lau is the current ALE master.
15a | Uninstall | 1. Go to Windows' Add/Remove Programs list in its control panel. 2. Ensure there is no NSO listed. 3. To manually uninstall that YOP uses, run "X:\Program Files\Common Files\Symantec Shared\SymSetup\{5AA2CD16-706F-41f3-87C5-2B5A031F2B3B}_10_2_0_<build #>\{5AA2CD16-706F-41f3-87C5-2B5A031F2B3B}.exe" 4. Reboot as requested. 5. Windows should be without NSO. | 1.-2. NSO uninstall is not there. 3. Uninstall should work. This is a loud uninstall. 4. Reboot when asked. Ensure no problems in shut down and reboot. 5. Should be no errors, no crashes, no problems, etc. | 10 | No silent uninstalls due to security reasons according to Julio Cullear on 10/31/2006.
15b |  | 1. After uninstalling, check for left overs on HDD, in IE, etc. 2. Use InstallCheck tool to check for these left over files and registry. | No left overs should be there. There might be a few things that can stay. | 15